## Sheet1
Issues | Raised By | Status | Action | ETA
A full and comprehensive grey/white box penetration test leveraging both automated tools and manual analysis | Keith | WIP(already communicated to Partner) | Mynd | 2019-04-12
Mynd to share VAPT report | Darrell /Keith | Interim report is ready waiting for final report | Mynd | 2019-04-12
Final Testing report | Keith/Prabhakar | WIP | Mynd | TBD
Encrypt user id as a separate cookie and incorporate safety net to validate this cookie with the user id stored in the app session on every html request processed by the server | Prabhakar | WIP(Dev team working on it) | Mynd | 2019-04-11
Results of the longevity and stress test with Fidelity | Prabhakar | WIP | Mynd | TDB
JMeter scripts and validation scripts used during testing | Prabhakar | Done(Shared with test data) | Mynd | Done
MYND to share sample logs for each MYND operation with Fidelity ops team (Darrell team). Fidelity Ops team to make sure enough logging is captured so that in future we can use them for diagnosis. | Prabhakar | TBD | Mynd | 2019-04-11
Fidelity to engage Performance team to run the Jmeter test scripts and independently validate the results to make sure the fix worked and session mangling did not happen on high volumes | Prabhakar |  | Fidelity
Mynd to share logs with screen shots to enable Fidelity security ops to analyze the logs for any security vulnerability including wrong session access | Prabhakar | WIP | Mynd | 2019-04-11